## Support
source : michaellant.com/2010/06/04/five-simple-steps-to-agile-risk-management/ |  |  |  | Agile Risk Management
| 1.Identify |  |  |  | 2.Classify |  |  |  | 3.Quantify |  | US fulfillment Fail risk Quantification
Name Proposals for Investigation tool
[10 empty] | 5 | 5 | 10 | 15 | 20 | 25 |  |  |  |  | Quantification weights
[16 empty] | Key words | Synonyms |  |  | 10% | 20% | 30% | 40%
[16 empty] | Investigation | Spying/Spy |  | Names | Readability | Spelling | Lenght | Meaning | Qtfct° ( /4)
[10 empty] | 4 | 4 | 8 | 12 | 16 | 20 | Variables | Data/tags |  | Netspy | ++++ | ++++ | ++++ | +++ | 3.6
[16 empty] | CIP | Ethernet Network |  | DataSpy | ++++ | ++++ | ++++ | +++ | 3.6
[16 empty] | VS |  |  | Ethspy | ++++ | ++ | ++++ | ++ | 2.8
[10 empty] | 3 | 3 | 6 | 9 | 12 | 15 | Tool | Software |  | Train Network Data Processor | + | +++ | + | ++++ | 2.6
[16 empty] | Train | --- |  | TrainSpy | ++++ | ++++ | ++++ | ++ | 3.2
[16 empty] | Alstom | --- |  | Tag Processor | +++ | ++++ | +++ | +++ | 3.2
[10 empty] | 2 | 2 | 4 | 6 | 8 | 10 | Test | --- |  | Network Data Displayer | +++ | +++ | ++ | ++++ | 3.1
[16 empty] | Visualization | Display |  | Tag Extractor | +++ | ++++ | +++ | +++ | 3.2
[16 empty] | Treatment | Processing |  | Network Spying tool | +++ | +++ | ++ | ++++ | 3.1
[10 empty] | 1 | 1 | 2 | 3 | 4 | 5 | Monitor | ---- |  | Tag Monitor | +++ | +++ | +++ | +++ | 3
[16 empty] | Traffic | ---- |  | Traffic Spy | +++ | ++++ | +++ | ++++ | 3.6
[16 empty] | Frames | ---- |  | Traffic Monitor | +++ | ++++ | +++ | +++ | 3.2
[11 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  | Traffic Data Processor | +++ | ++++ | ++ | ++++ | 3.3
[19 empty] | Alstom NetSpy | ++ | +++ | +++ | ++ | 2.5
[19 empty] | DaNetSpy | +++ | ++ | ++++ | + | 2.3
[19 empty] | ProNetVar | +++ | ++ | ++++ | + | 2.3
Alstom TraINvesT
NetProbe
s
|  | 6.Repeat |  |  |  | 5.Act |  |  | 4.Plan
Agile T-shirt Sizing Estimation method
|  |  | XS | S | M | L | XL | XXL
P R O B A B I L I T Y
I M P A C T
US1
US2
US3
US4
US5
US6
US7
US8
US9
US10
US11
US12
US13
US14
US16
US15
US17
US18
US20
US19

## Product Backlog
1 | 2 | 3 | 5 | 8 | 13 | 21 | 34 | 55 | Epic
[10 empty] | Risk Management |  |  |  | Priority
ID | Product Backlog Item |  |  | User Story | [5 empty] | Identification | Quantification | Action Plan if problems are encountered |  | T-Shirt Sizing | Dependancy | Effort (Poker Planning) | Comments | Planned in Sprint
US1 | New project creation |  |  | As a user, I want to create a new project so that I could swap easily from one project to another | [5 empty] | Strenghts | 5 |  | No explicit Action Required | XL | US3/US4 | 5 | Thinkings must be done about what a project creation consists of, the created files and information they save
US2 | Environment selection |  |  | As a user, I want to Select the environment (VS/CIP) so that I could configure the tool about the network to spy on | [5 empty] | Strenghts | 4 |  | No explicit Action Required | S | None | 1 | GUI utilities
US3 | CIP Project file import |  |  | As a user, I want to Import the CIP project file so that the tool could know which tags contain the frames after formatting the project file | [5 empty] | Weaknesses | 10 |  | Self Training | M | US2 | Epic | CIP Protocol is unknown and complex, that involves a high risk and great Effort
US4 | VS Project file import |  |  | As a user, I want to Import the VS project file so that the tool could know which tags contain the frames after formatting the project file | [5 empty] | Weaknesses | 10 |  | Self Training | L | US2 | 13 | VS Protocol is unknown but less complex ; that involves risks but less effort than CIP protocol
US5 | Project file backup |  |  | As a user, I want to Save the project file so that I can use it later to open an existing project | [5 empty] | Strenghts | 3 |  | No explicit Action Required | XL | US1 | 1 | Defined Libraires use
US6 | Existing project launch |  |  | As a user, I want to Open an existing project so that I could pursue investigating about the last traffic without importing manually again the project file | [5 empty] | Strenghts | 4 |  | No explicit Action Required | XL | US1 | 1 | GUI utilities + Scripts
US7 | CIP Data traffic sniffing |  |  | As a user, I want to Spy CIP traffic so that I could listen to data frames being exchanged and display them as they are exchanged (brut) | [5 empty] | Weaknesses | 25 |  | Self Training + Exchanges with Soft. Dev. Colleagues | M | US1/US6 | epic | CIP Protocol appropriation may take way much time than VS protocol's ; that involves a maximum risk and Great Effort
US8 | VS Data traffic sniffing |  |  | As a user, I want to Spy VS traffic so that I could listen to data frames being exchanged and display them as they are exchanged (brut) | [5 empty] | Weaknesses | 25 |  | Self Training + Exchanges with Soft. Dev. Colleagues | L | US1/US6 | 8 | Vs network data Sniffing easier than CIP network, but the risk remains maximum and great efforts have to be produced
US9 | Data processing |  |  | As a user, I want to Process the data so that I could extract variables’ value and type from the data frames | [5 empty] | Weaknesses | 20 |  | Self Training + Exchanges with Soft. Dev. Colleagues | S | US7/US8 | 34 | Consists of cutting the frames, extracting the useful information , so the amount of job is considerable
US10 | Variables backup |  |  | As a user, I want to Save variables so that I could display them in live but also have them backed up in case I want to view them offline | [5 empty] | Strenghts | 5 |  | No explicit Action Required | M | US9 | 1 | GUI utilities + Database Management
US11 | CIP Variables display |  |  | As a user, I want to Display CIP variables so that I could see their value, type and eventually more details in order to check or solve something | [5 empty] | Strenghts | 5 |  | No explicit Action Required | S | US13 | 1 | GUI utilities + Database Management
US12 | VS Variables display |  |  | As a user, I want to Display VS variables so that I could see their value, type and eventually more details in order to check or solve something | [5 empty] | Strenghts | 5 |  | No explicit Action Required | M | US13 | 1 | GUI utilities + Database Management
US13 | Variable add |  |  | As a user, I want to Add a variable so that I could display a new variable taken from the processed data | [5 empty] | Strenghts | 3 |  | No explicit Action Required | S | US10 | 1 | GUI utilities + Database Management
US14 | Variable removal |  |  | As a user, I want to Delete a variable so that I could take off a variable from the Dashboard | [5 empty] | Strenghts | 3 |  | No explicit Action Required | S | US11/US12 | 1 | GUI utilities + Database Management
US15 | Variable tracing |  |  | As a user, I want to be able to Draw a variable’s evolution so that I could see the variations of its value in the time | [5 empty] | Strenghts | 6 |  | Self Training | S | US11/US12 | 2 | Graphic libraries use
US16 | Variable customisation |  |  | As a user, I want to customize a variable so that I could highlight it or discriminate it from other variables | [5 empty] | Strenghts | 6 |  | Self Training | S | US11/US12 | 2 | Graphic libraries use
US17 | Fugitive variations detection |  |  | As a user, I want to Detect fugitive variations so that the system could let me know when a variable's value fluctuate so quickly that i couldn't see it. | [5 empty] | Strenghts | 6 |  | Self Training | S | US11/US12 | 2 | Scripts to compare diferent states of a variable in time
US18 | Dashboard export |  |  | As a user, I want to export the dashboard so that I could share the observations with someone else or use them later | [5 empty] | Strenghts | 2 |  | No explicit Action Required | XS | None | 1 | GUI utilities
US19 | Snapshot taking |  |  | As a user, I to Take a Snapshot so that I could export the content of the dashboard in the pc's clipboard and feel free to paste it in a text editor | [5 empty] | Strenghts | 4 |  | No explicit Action Required | XS | US18 | 1 | Defined Libraires use
US20 | CSV file creation |  |  | As a user, I want to create as .csv file so that I could export the content of the dashboard in a file with a csv extension | [5 empty] | Strenghts | 4 |  | No explicit Action Required | S | US18 | 1 | Defined Libraires use

## Sprint 1(23 Avril-4 Mai)
Development | Developped User Stories
| ID | User Story | Effort | Durat° (days) | Start date | End date
| US8 | As a user, I want to Spy VS traffic so that I could listen to data frames being exchanged and display them as they are exchanged (brut) | 8 | 2
| US1 | As a user, I want to create a new project so that I could swap easily from one project to another | 5 | 1
| US4 | As a user, I want to Import the VS project file so that the tool could know which tags contain the frames after formatting the project file | 13 | 3
| US5 | As a user, I want to Save the project file so that I can use it later to open an existing project | 1 | 1