## Support
source : michaellant.com/2010/06/04/five-simple-steps-to-agile-risk-management/ |  |  |  | Agile Risk Management
| 1.Identify |  |  |  | 2.Classify |  |  |  | 3.Quantify |  | US fulfillment Fail risk Quantification
Name Proposals for Investigation tool
[10 empty] | 5 | 5 | 10 | 15 | 20 | 25 |  |  |  |  | Quantification weights
[16 empty] | Key words | Synonyms |  |  | 10% | 20% | 30% | 40%
[16 empty] | Investigation | Spying/Spy |  | Names | Readability | Spelling | Lenght | Meaning | Qtfct° ( /4)
[10 empty] | 4 | 4 | 8 | 12 | 16 | 20 | Variables | Data/tags |  | Netspy | ++++ | ++++ | ++++ | +++ | 3.6
[16 empty] | CIP | Ethernet Network |  | DataSpy | ++++ | ++++ | ++++ | +++ | 3.6
[16 empty] | VS |  |  | Ethspy | ++++ | ++ | ++++ | ++ | 2.8
[10 empty] | 3 | 3 | 6 | 9 | 12 | 15 | Tool | Software |  | Train Network Data Processor | + | +++ | + | ++++ | 2.6
[16 empty] | Train | --- |  | TrainSpy | ++++ | ++++ | ++++ | ++ | 3.2
[16 empty] | Alstom | --- |  | Tag Processor | +++ | ++++ | +++ | +++ | 3.2
[10 empty] | 2 | 2 | 4 | 6 | 8 | 10 | Test | --- |  | Network Data Displayer | +++ | +++ | ++ | ++++ | 3.1
[16 empty] | Visualization | Display |  | Tag Extractor | +++ | ++++ | +++ | +++ | 3.2
[16 empty] | Treatment | Processing |  | Network Spying tool | +++ | +++ | ++ | ++++ | 3.1
[10 empty] | 1 | 1 | 2 | 3 | 4 | 5 | Monitor | ---- |  | Tag Monitor | +++ | +++ | +++ | +++ | 3
[16 empty] | Traffic | ---- |  | Traffic Spy | +++ | ++++ | +++ | ++++ | 3.6
[16 empty] | Frames | ---- |  | Traffic Monitor | +++ | ++++ | +++ | +++ | 3.2
[11 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  | Traffic Data Processor | +++ | ++++ | ++ | ++++ | 3.3
[19 empty] | Alstom NetSpy | ++ | +++ | +++ | ++ | 2.5
[19 empty] | DaNetSpy | +++ | ++ | ++++ | + | 2.3
[19 empty] | ProNetVar | +++ | ++ | ++++ | + | 2.3
Alstom TraINvesT
NetProbe
s
|  | 6.Repeat |  |  |  | 5.Act |  |  | 4.Plan
Agile T-shirt Sizing Estimation method
|  |  | XS | S | M | L | XL | XXL
P R O B A B I L I T Y
I M P A C T
US1
US2
US3
US4
US5
US6
US7
US8
US9
US10
US11
US12
US13
US14
US16
US15
US17
US18
US20
US19

## Product Backlog
1 | 2 | 3 | 5 | 8 | 13 | 21 | 34 | 55 | Epic
[10 empty] | Risk Management |  |  |  | Priority
ID | Product Backlog Item |  |  | User Story | [5 empty] | Identification | Quantification | Action Plan if problems are encountered |  | T-Shirt Sizing | Dependancy | Effort (Poker Planning) | Comments | Planned in Sprint
US1 | New project creation |  |  | As a user, I want to create a new project so that I could swap easily from one project to another | [5 empty] | Strenghts | 5 |  | No explicit Action Required | XL | US3/US4 | 5 | Thinkings must be done about what a project creation consists of, the created files and information they save
US2 | Environment selection |  |  | As a user, I want to Select the environment (VS/CIP) so that I could configure the tool about the network to spy on | [5 empty] | Strenghts | 4 |  | No explicit Action Required | S | None | 1 | GUI utilities
US3 | CIP Project file import |  |  | As a user, I want to Import the CIP project file so that the tool could know which tags contain the frames after formatting the project file | [5 empty] | Weaknesses | 10 |  | Self Training | M | US2 | Epic | CIP Protocol is unknown and complex, that involves a high risk and great Effort
US4 | VS Project file import |  |  | As a user, I want to Import the VS project file so that the tool could know which tags contain the frames after formatting the project file | [5 empty] | Weaknesses | 10 |  | Self Training | L | US2 | 13 | VS Protocol is unknown but less complex ; that involves risks but less effort than CIP protocol
US5 | Project file backup |  |  | As a user, I want to Save the project file so that I can use it later to open an existing project | [5 empty] | Strenghts | 3 |  | No explicit Action Required | XL | US1 | 1 | Defined Libraires use
US6 | Existing project launch |  |  | As a user, I want to Open an existing project so that I could pursue investigating about the last traffic without importing manually again the project file | [5 empty] | Strenghts | 4 |  | No explicit Action Required | XL | US1 | 1 | GUI utilities + Scripts
US7 | CIP Data traffic sniffing |  |  | As a user, I want to Spy CIP traffic so that I could listen to data frames being exchanged and display them as they are exchanged (brut) | [5 empty] | Weaknesses | 25 |  | Self Training + Exchanges with Soft. Dev. Colleagues | M | US1/US6 | epic | CIP Protocol appropriation may take way much time than VS protocol's ; that involves a maximum risk and Great Effort
US8 | VS Data traffic sniffing |  |  | As a user, I want to Spy VS traffic so that I could listen to data frames being exchanged and display them as they are exchanged (brut) | [5 empty] | Weaknesses | 25 |  | Self Training + Exchanges with Soft. Dev. Colleagues | L | US1/US6 | 8 | Vs network data Sniffing easier than CIP network, but the risk remains maximum and great efforts have to be produced
US9 | Data processing |  |  | As a user, I want to Process the data so that I could extract variables’ value and type from the data frames | [5 empty] | Weaknesses | 20 |  | Self Training + Exchanges with Soft. Dev. Colleagues | S | US7/US8 | 34 | Consists of cutting the frames, extracting the useful information , so the amount of job is considerable
US10 | Variables backup |  |  | As a user, I want to Save variables so that I could display them in live but also have them backed up in case I want to view them offline | [5 empty] | Strenghts | 5 |  | No explicit Action Required | M | US9 | 1 | GUI utilities + Database Management
US11 | CIP Variables display |  |  | As a user, I want to Display CIP variables so that I could see their value, type and eventually more details in order to check or solve something | [5 empty] | Strenghts | 5 |  | No explicit Action Required | S | US13 | 1 | GUI utilities + Database Management
US12 | VS Variables display |  |  | As a user, I want to Display VS variables so that I could see their value, type and eventually more details in order to check or solve something | [5 empty] | Strenghts | 5 |  | No explicit Action Required | M | US13 | 1 | GUI utilities + Database Management
US13 | Variable add |  |  | As a user, I want to Add a variable so that I could display a new variable taken from the processed data | [5 empty] | Strenghts | 3 |  | No explicit Action Required | S | US10 | 1 | GUI utilities + Database Management
US14 | Variable removal |  |  | As a user, I want to Delete a variable so that I could take off a variable from the Dashboard | [5 empty] | Strenghts | 3 |  | No explicit Action Required | S | US11/US12 | 1 | GUI utilities + Database Management
US15 | Variable tracing |  |  | As a user, I want to be able to Draw a variable’s evolution so that I could see the variations of its value in the time | [5 empty] | Strenghts | 6 |  | Self Training | S | US11/US12 | 2 | Graphic libraries use
US16 | Variable customisation |  |  | As a user, I want to customize a variable so that I could highlight it or discriminate it from other variables | [5 empty] | Strenghts | 6 |  | Self Training | S | US11/US12 | 2 | Graphic libraries use
US17 | Fugitive variations detection |  |  | As a user, I want to Detect fugitive variations so that the system could let me know when a variable's value fluctuate so quickly that i couldn't see it. | [5 empty] | Strenghts | 6 |  | Self Training | S | US11/US12 | 2 | Scripts to compare diferent states of a variable in time
US18 | Dashboard export |  |  | As a user, I want to export the dashboard so that I could share the observations with someone else or use them later | [5 empty] | Strenghts | 2 |  | No explicit Action Required | XS | None | 1 | GUI utilities
US19 | Snapshot taking |  |  | As a user, I to Take a Snapshot so that I could export the content of the dashboard in the pc's clipboard and feel free to paste it in a text editor | [5 empty] | Strenghts | 4 |  | No explicit Action Required | XS | US18 | 1 | Defined Libraires use
US20 | CSV file creation |  |  | As a user, I want to create as .csv file so that I could export the content of the dashboard in a file with a csv extension | [5 empty] | Strenghts | 4 |  | No explicit Action Required | S | US18 | 1 | Defined Libraires use

## Sprint 1(23 Avril-4 Mai)
Development | Developped User Stories
| ID | User Story |  |  |  | Effort | Durat° (days) | Start date | End date | Comments
| US8 | As a user, I want to Spy VS traffic so that I could listen to data frames being exchanged and display them as they are exchanged (brut) |  |  |  | 8 | 2 | 2018-04-24 | 2018-04-25 | finished the 26/04/2018
| US1 | As a user, I want to create a new project so that I could swap easily from one project to another |  |  |  | 5 | 1 | 2018-04-26 | 2018-04-26
| US4 | As a user, I want to Import the VS project file so that the tool could know which tags contain the frames after formatting the project file |  |  |  | 13 | 3 | 2018-04-27 | 2018-05-03
| US5 | As a user, I want to Save the project file so that I can use it later to open an existing project |  |  |  | 1 | 1 | 2018-05-04 | 2018-05-04
Tests & Validation | US ID | Scénario | Steps | Action | Inputs |  |  | Expected Outputs
| US8 |  | 0 | Initial State : U-test Data Exchange Running, NetProbe Compiled and Launched | None |  |  | None
|  |  | 1 | Connect NetProbe to the Network and Read Data | Click on Connect Button |  |  | Display of Brut Frames being exchanged
|  |  | 2 | Observation of Variable's value Change | Change Variables' value on U-Test |  |  | Notice Frames' value change on NetProbe
|  |  | 3 | Close NetProbe 1/3 | Click on the "X" Button at the upper right corner |  |  | Pop UP Window Appears, asking Are you sure you want to close (Yes/No)
|  |  | 4 | Close NetProbe 2/3 | Click On "No" button |  |  | Return To Data Display View on NetProbe
|  |  | 5 | Close NetProbe 3/3 | Click On "X" then "Yes" Buttons |  |  | Close NetProbe Execution Window
| US1 |  | 0 | Initial State : U-test Data Exchange Running, NetProbe Compiled and Launched | None |  |  | None
|  |  | 1 | Openning the New Project Creation Assistant | Click on "Create A new Project" Button |  |  | Pop Up Window Appearance, Asking to Name Project & import of the project file
|  |  | 2 | Closing the Project Creation Window | Click on "Close" Button |  |  | Close Project Creation Window and go to NetProbe Home Window
|  |  | 3 | Naming the Project (Reopen New Project assistant First) | Enter the name in the defined Text area |  |  | Acceptance Message if name Format is correct, Error message if not
|  |  | 4 | Creating the project | Click on "Create Project" (Name is Correct and project file is imported) |  |  | Creation and backup of the new Project File and Dashboard display
| US4 |  | 0 | Initial State : U-test Data Exchange Running, NetProbe Compiled and New project creation assistant opened | None |  |  | None
|  |  | 1 | Indicating the location of the project file | Click on "Browse" Button and select the file in the directory it's located in |  |  | Display of the project file's path in the defined text area
|  |  | 2 | Processing the project file | Click on "Create project" (Name is Correct and project file is imported) |  |  | Processing of the project file and creation of corresponding tables in the database
| US5 |  | 0 | Initial State : U-test Data Exchange Running, NetProbe Compiled and New project creation assistant opened | None |  |  | None
|  |  | 1 | Saving the project file | Click on "Create Project" (Name is Correct and project file is imported) |  |  | Creation of a project file's copy with the same name as the project
Initial State
NetProbe Connection
Noticing Variables' change
Validate Closure
Close NetProbe
Abort Closure
Initial State
Open New Project Assistant
Close New Project Assistant
Name Project
Create the Project
Initial State
Locate the project file
Process the Project File
Initial State
Save the project file